## Sheet1
RBM Malaria in Pregnancy Working Group Workplan, 2017-2018
| Activities | Responsible Partner/ Contributing Partner | Timeline | Progress Update
1 | Advocacy
1.1 | Advocate for availability of quality assured SP supply at global level and point of care, and advocate for QA SP and low dose folic to be included in Essentials Medicine List | Chemonics, TIPTOP, WHO, MMV, Julie Gutman
1.2 | Support national TWGs, NMCPs and RH Departments in the application of the WHO 2016 Recommendations on antenatal care for a positive pregnancy, including through promotion and dissemination of the RBM MiP ANC brief. | All partners | Ongoing
1.3 | Hold meeting focused on MiP programming and strategy in low transmission regions | The Global Fund | Q2
1.4 | Raise the profile of MiP case management and the continuum of care for severe malaria in pregnant women through dissemination of case management job aid to countries | MCSP | Q1/Q2
1.5 | Promote greater integration of MiP in investment pieces through the Global Funding Facility | The Global Fund | Ongoing
1.6 | Advocate for community based programming, community engagement and the potential to successfully expand coverage and reach the hardest to reach populations | Unitaid/TIPTOP, PMI, MCSP | Ongoing
2 | Products and Tools
2.1 | Support dissemination of existing tools: SBCC Implementation Kit, Case Management Job Aid, Toolkit for early assessment of gestational age, IPT quality assurance checklist. Share tools through MiP WG website and the CRSPC | All partners | Ongoing
2.2 | Finalize and disseminate MiP country profiles | PMI/MCSP/GF | Q1/Q2
2.3 | Develop and disseminate MiP M&E Brief | MCSP/PMI/MERG/CDC/WHO
2.4 | Perform webinar to support promotion and utilization of products & tools such as the CM Job Aid, IPTp toolkit, etc. | MCSP, PMI
3 | Support of country-level implementation
3.1 | Build capacity of providers in case management of MiP around the new ANC guidelines, using tools such as the case management job aid for training, supportive supervision, etc. | All partners | Q1/Q2
3.2 | Disseminate MiP tools and products to countries through the CRSPC | co-Chairs | Ongoing
3.3 | Document and disseminate country best practices and lessons learned in MiP programming | All partners | Ongoing
4 | Coordination & Collaboration
4.1 | Strengthen engagement with the RBM Partnership through participation in the Steering Committee | Co-chairs | Ongoing
4.2 | Convene MIP WG annual meeting | Co-chairs/Secretariat | ?
4.3 | Continue collaboration and improve coordination with other WGs such as the Social Behavior Change Communication (SBCC) MiP Sub Task Force, the Monitoring and Evaluation Working Group (through the MiP M&E brief), etc. | All partners | Ongoing
4.4 | Invite the Vector Control WG to participate in WG meetings to provide updates on ITNs, insecticide resistance issues, etc. | Co-chairs | Q1
4.5 | Create a forum, such as a Community of Practice, in which the application of global strategies can be discussed and shared by countries
5 | Research Opportunities/Priorities
5.1 | Continue to research HS-RDTs for asymptomatic pregnant women and for non-falciparum | Gates, FIND | Ongoing
5.2 | Gather evidence on C-IPTp approach for improving IPTp uptake | TIPTOP, CDC, PMI, MCSP | Ongoing
5.3 | Conduct a clinical trial on the safety and efficacy of alternatives to SP in areas of high SP resistance | CDC, PMI, LSTM | Ongoing